## Ambulance
Ambulance V.1
Admin
No | Component | Activity | Remarks | Question | Completed | Not Completed
1 | Dashboard
| Total Ambulance |  | Integration Needed
| Total Staff |  | Integration Needed
| This Week Earning |  | Integration Needed
| Total Earning |  | Integration Needed
Recent Trip
| Graph Visit This Week |  | Integration Needed
| Graph Visit Chamber Wise |  | Integration Needed
Navbar
| Header |  | EHC Header Required
Notification
Chat
My Profile
Sidebar
2 | Company Registration
3 | Ambulances
Ambulance Details
Add New Ambulance
4 | Staff
Staff Details
Add New Staff
5 | Locate Ambulance
6 | Trip History
Dashboard
1 | Dashboard
| Trip Today |  | Integration Needed
| Trip This Week |  | Integration Needed
| This Week Earning |  | Integration Needed
| Total Earning |  | Integration Needed
New Booking => Confirm
| Graph Trip History for This Week |  | Integration Needed
| Graph Trip History for Last 6 Months |  | Integration Needed
Navbar
| Header |  | EHC Header Required
Notification
Chat
My Profile
2 | Manual Booking
3 | Trip History
4 | Locate Ambulance
5 | Complaint

## Pharmacy
Pharmacy V.1
Admin
No | Component |  | Activity | Remarks | Question | Completed | Not Completed
1 | Dashboard
| Order This Week | version will upgrade itself as the system will learn more |  | Integration Needed
| Current Stocks |  |  | Integration Needed
| Sold Stocks |  |  | Integration Needed
| Expired Stocks |  |  | Integration Needed
| Total Pharmacy |  |  | Integration Needed
| Total Staff |  |  | Integration Needed
| Earned This Week |  |  | Integration Needed
| Earned Total |  |  | Integration Needed
| Recent Activity |  |  | Integration Needed
| Recent Order |  |  | Integration Needed
| Graph Visit This Week |  |  | Integration Needed
| Graph Visit Chamber Wise |  |  | Integration Needed
Navbar
| Header |  |  | EHC Header Required
Notification
Chat
My Profile
Sidebar
2 | Pharmacy
Pharmacy Details
Add New Pharmacy
3 | Staff
Staff Details
Add New Staff
4 | Txn History
5 | Logistics
Stocks In Hand
Expired Product
Stocks Sold
6 | Analytics |  |  | Integration Needed
7 | Complaint |  |  | No Page
Dashboard
1 | Dashboard
| Order Today |  |  | Integration Needed
| Order This Week |  |  | Integration Needed
| Current Stocks |  |  | Integration Needed
| Sold Stocks |  |  | Integration Needed
| Expired Stocks |  |  | Integration Needed
| Earned Today |  |  | Integration Needed
| Earned This Week |  |  | Integration Needed
| Earned Total |  |  | Integration Needed
| New Order => Details |  |  | Integration Needed
| Confirm Order |  |  | Integration Needed
| Graph Visit This Week |  |  | Integration Needed
| Graph Visit Chamber Wise |  |  | Integration Needed
Navbar
| Header |  |  | EHC Header Required
Notification
Chat
My Profile
2 | Offlien Order
3 | Order History
4 | Logistics
Upload Stocks
Stocks In Hand
Expired Product
Stocks Sold
5 | Analytics |  |  | Integration Needed
6 | Complaint |  |  | No Page

## Blood Bank
Blood Bank V.1
No | Component | Activity | Remarks | Question | Completed | Not Completed
1 | Dashboard
| Trip Today |  | Integration Needed
| Trip This Week |  | Integration Needed
| This Week Earning |  | Integration Needed
| Total Earning |  | Integration Needed
| Graph Trip History for This Week |  | Integration Needed
| Graph Trip History for Last 6 Months |  | Integration Needed
Navbar
| Header |  | EHC Header Required
Notification
Chat
My Profile
Sidebar
2 | Company
Company Details
Company Registration
3 | Donor
Donor Details
Register New Donor
4 | Inventory
5 | ERP |  | Integration Needed
6 | CRP |  | Integration Needed

## Doctor
Doctor V.1
No | Component | Activity | Remarks | Question | Completed | Not Completed
1 | Dashboard
| Todays Appointment |  | Integration Needed
| This Week Appointment |  | Integration Needed
| This Week Earning |  | Integration Needed
| Total Earning |  | Integration Needed
New Appointment => Check
Chamber Wise Appointment => Visit Patient
Patient Visit Report => Prepare Pescription
Prepare Pescription
| Graph Visit This Week |  | Integration Needed
| Graph Visit Chamber Wise |  | Integration Needed
Navbar
| Header |  | EHC Header Required
Notification
Chat
My Profile
Sidebar
2 | Chamber
Chamber Details
Chamber Registration
3 | Patient History
Pateint Name => Patient Profile
4 | Visit Outside Patient
5 | Analytics |  | Integration Needed
On Click => Shwo Big Analytcis
6 | Emergency |  | No Page
7 | Machine Dignostic |  | No Page

## Delivery System
Delivery System V.1
No | Component | Activity | Remarks | Question | Completed | Not Completed
1 | Dashboard
Navbar
| Header |  | EHC Header Required
Notification
Chat
My Profile
Sidebar
2 | New Order |  | Integration Needed
3 | Locate Order |  | Integration Needed
4 | Order Hsitory |  | Integration Needed

## PatientCustomer
Patient/Customer V.1
No | Component |  | Activity | Remarks | Question | Completed | Not Completed
1 | Index
Offer Banner
Offer Banner
| Order Medicine | V3
Health Care Products
Dignostic Test
Doctor Consultation
Ambulance
Category => Show All
All Category
Top Selling Product
Hospital => Read More
Hospital List
Health Concern =>More
Doctor List
EHC Feature
More Product => Show All
Product Page
Navbar
| Sign In/Sign Up |  |  | EHC Header Required
UserName =>
My Profile
Orders
Billing History
Diagonostic History
Appointment History
Cart
| Order Medicine | V3
Health Care Products =>
All Category =>
Product Page =>
| Product Description => | V3
Cart =>
Checkout =>
Payment Page =>
Thank You
Dignostic Test
Doctor Consultation =>
Confirm Appointement
Ambulance
Sidebar
2 | Blood Bank | V2 |  | Integration Needed
3 | Locate Hospital |  |  | Integration Needed
4 | Physio/Gym |  |  | No Page
5 | Feedback |  |  | No Page
6 | Care Giver |  |  | No Page
Footer
7 | Company
Abou EHC
Contact
Career
Blog
Investors
8 | Our Service
Order Medicine
Health Care Products
Dignostic Test
Doctor Consultation
Ambulance
9 | Help
FAQ
Return Policy
Terms and Conditions
Privacy Policy
Feedback
10 | Categoies
11 | Follow Us
12 | Payment Partner

## Hospital
Hospital Layout 1
No | Component | Sub Component | Activity | Remarks | Question | Completed | Not Completed
1 | Super Admin
OPD
IPD
| Medical Department | New Patient
Department
Doctor
| Nurshing Department | New Patient
Bed Status
Doctor Avaliable
Nurse Avaliable
| Paramedical Department | Bacteriology Laboratory
Biochemistry
Haematology Laboratory
Parasitology Laboratory
Serology Laboratory
Blood Bank
Histopathology Department
P.M.R Department
Operation Theatre Complex (OT)
| Pharmacy Department | Meds Registration
Meds Inventory
Meds Purchase Bill
Meds Purchase History
Radiology Department (X-ray)
Dietary Department
Non-professional Services
| Medical Record Department (MRD) | OP Records
IP Records
Medicolegal Records
| Personnel Department | New Recruitment
Health Workers
Interview
Promotion & Transfer
Termination
Salary & Incentive
Health Programme
| Purchasing Department | Accounts
Housekeeping
Laundry
Mechanical Department
Maintenance Department
Central Supply Department
Social Service
Pastoral Care
Hospital Waste Management
C.S.S Department
ER
Ambulance
Navbar
No Header
Sidebar
Side Bar
Hospital Layout 2
No | Component | Sub Component | Activity | Remarks | Question | Completed | Not Completed
1 | Admin | Add Senior Admin
Avaliable Senior Admin
2 | Account Admin | Add User
Avaliable User
3 | Floor Codrinator Admin | Add User
Avaliable User
4 | GRE Admin | Patient Registration
5 | HR Admin | Add User
Avaliable User
6 | Medical Admin | Add User
Avaliable User
Take Intervie
RMO
Patient Medical History
7 | Nurse Admin | Add User
Avaliable User